## Summary-GroupIterationProgress
Team 1 - trackr
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 05/10 - 05/17 | 1. Completed all deliverables for Iteration 0 2. Skeleton Spring Boot application and Swagger Document | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 81 | 79 | 2 | 39 | 7 | 0 | 8 | 3 | 14 | 8 | 0
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Timothy Flucker | Developed Sections 1, 2, 3, 6b | Created initial tasks for Iteration 0 activities and Lab1. | N/A | N/A | Helped create initial slide deck and provide content from my assigned SPPP sections. | Committed a basic Spring application which is to be used as a starting point for Iteration 1 development. | Created basic unit test in committed code to be used a reference for other team members. | N/A | Assisted Jean by providing standup updates and comments on documents. Helped setup Discord threads for Standup Notes and PR Requests to increase team organization.
Xiaobing Hou | Developed Section 5
Jean Dorancy | Management Plan, Git Branching Strategry, Code Review Process | Created cores related to iteration 0 and completed them. | N/A | N/A | Completed the slide deck. Recorded presentation video. | N/A | N/A | Created reposiotry, configured branch proctetion rules and merging strategy. Also added .gitignore file and Pull Request template. Peformed code reviews. | General coodination for the team. Organized meetings (sending invites). Drived meetings agenda. Daily Scrum (in appropriate thread). Drived discussions. | N/A
Weijie Liang | Developed Section 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## Jean Dorancy
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 23 | 21 | 2 | 0 - Studied the course module and watched all the videos. 1 - Reviewed and discussed project requirements proposed by Tim 5 - Coodinated team meetings, Work on SPPP, Risk Management, Estimation and presentation. 6 - Setup Git repository with merge and protection rules. | 8 | 2 | 0 | 0 | 0 | 10 | 1 | 0 | 1. Write 3 sections of SPPP 2. Completed Lab 1 3. Completed project presentation 4. Completed risk management sheet 5. Created estimation sheet 6. Created Pull Request Template | 1. It's was quite a bit of materials to study | 1. Frontload module stuying early in the week | 0 - Organize Sprint Planning for iteration 1 1 - Study Module 2 3 - Work on implementation after tasks assignments | 35

## Timothy Flucker
Your Lead Roles: Backup Project Leader, Design and Implementation Leader + Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/15 | 20 | 18 | 2 | 0 - Reviewing course materials and documents, read module notes + chapters 1 - Define High-level requirements based on initial project proposal to team 3 - Created Spring Boot "Hello World" application 4 - Developed basic unit test in "Hello World" application 5 - Created Discord threads, and provided regular updates | 10 | 5 | 0 | 8 | 1 | 1 | 0 | 0 | 1. Wrote 3 sections of SPPP 2. Committed code for "Hello World" Spring Boot application 3. Provided content and comments for Iteration 0 presentation. 4. Created Discord threads and participated in group discussions and meetings. |  |  | 0 - Continue with module notes and reviewing course materials 1 - Define Requirements for Iteration 1, input these into PivotalTracker 2 - Create design document template for team to use 3 - Develop Iteration 1 requirements related User Management, H2 Database configuration, and Bank Account Management 4 - Create more varied unit tests (api logic, validation, entity tests) 5 - Continue providing updates and comments as necessary. | 20
2 | 05/16 - 05/22
3 | 05/23 - 05/29
4 | 05/30 - 06/05
5 | 06/06 - 06/12
6 | 06/13 - 06/19

## Xiaobing Hou
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/15 | 25 | 12 | 2 | 0 - learn git, Spring boot framework, Heroku, read several tutorials 6 - set up git, IDE, java | 16 | 0 | 0 | 0 | 2 | 2 | 5 | 0 | 1. Write section5 for SPPP 2. Set up git, commit a test message on git |  |  | 0 - Continue with module notes and reviewing course materials 1 - Continue learn Spring Boot framework and Heroku 2 - Try to code use Spring Boot framework and do a simple program | 30

## Weijie Liang
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/15 | 8 | 7.5 | 0.5 | 0 - learn git and springboot, review class material, read Module 1 6 - set up git, Java | 5 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1. Write Section 6 of SPPP 2. Set up git, commit README.MD on git |  |  | 1. Continue reviewing class material and Modules 2. Learn about Springboot framework 3. Try to write basic Springboot based code | 28