## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2022-06-01 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | New students joined the team in the middle of development | 1 | 3 | 3 | 45 | team leader and all members | 2022-06-01 | Keep good project documentation New engineers will work with a dedicated senior engineer | No one has joined after we started | Open
| Lack of motivation or responsibility | One or more students are not actively participating in the project | 1 | 5 | 3 | 15 | team leader and all members | 2022-06-22 | Opportunities for everyone to learn Everyone to work on something they are interested Practice the sprint rituals which keeps the team engaged | Everyone is actively contributing so far | Open
Communication | duplicate work | Two or more students are working on the same tasks without coordination hence duplicated work. | 2 | 3 | 3 | 36 | Team Leader | 2022-06-22 | Create a detailed project plan and get buy-in from the team Assign tasks to individuals during Sprint Planning Every tasks in the Sprint is assigned to a specific person in PivotalTracker | No duplicated work so far | Open
| useless work | Students work cannot be used in the project. | 3 | 3 | 3 | 27 | team leader and all members | 2022-05-30 | Architecture and design session before we start big chuck of work Student to write design document about how they are going to implement a feature Students to break down feature work into small parts and complete them which will give enough opportunity to catch if we are build the product right | Development work has not started | Open
Requirements | unclear requirements | Requirements about a feature are not well understood. | 3 | 4 | 2 | 12 | team leader and all members | 2022-05-30 | Sprint review meeting with stakeholders Constant communication with stakeholders Stakeholders to review all requirements and answer questions. | Stakeholders review of requirements is pending | Open
| scope creep | Significant increase in the a feature scope than anticipated. | 4 | 4 | 4 | 16 | team leader and all members | 2022-05-30 | Meeting with stakeholders about increase of scope which might impact project schedule Dropping some of essential features Alternative technical solutions | Requirements are being determined | Open
| constant requirements changes | Stakeholders keep changing the project requirements. | 5 | 4 | 4 | 8 | team leader and all members | 2022-06-22 | Favor generic solutions so they are adaptable Embrace the change and build the product using appropriate design patterns Emphasize the communication with stakeholders to ensure requirements are well understood | Requirements are being determined | Open
Management | improper task assignments | Tasks assigned to team members does not fit their skillset or preferrence. | 3 | 3 | 3 | 27 | Team Leader | 2022-06-22 | Sprint planning meeting and discuss tasks before they are assigned | Planning phase | Open
| improper planning | No timeline or tasks breakdown | 1 | 2 | 3 | 60 | Team Leader | 2022-05-22 | Project scoping and estimation Detailed tasked break down | Planning phase | Open
Technology competence | Not familiar with the framework used | Team members who are not familiar with the framework and other techologies used to development project. | 2 | 3 | 3 | 36 | Design and Implementation Leader | 2022-05-22 | Plan time for tutorial about the framework No indroducing new techologies late in the project Use widely support technologies so students can find help online if they are blocked | We have selected the Spring framework and everyone on the team is somewhat familiar. Moreover, they all know Java. | Open
| Not familiar with unit testing | Students who are new to unit testing | 4 | 2 | 3 | 24 | QA Leader | 2022-06-04 | Plan time for unit testing tutorial (JUnit 5) Learn by doing as each feature implementation will require unit tests | Development work has not started | Open
Design and implementation | Improper design | Implemented a design that is not flexible or generic enough. | 3 | 4 | 3 | 18 | Design and Implementation Leader | 2022-06-22 | Architecture and design session before we start big chuck of work | Development work has not started | Open
Testing | Not enough testing | Falling short of the planned test coverage for the project | 3 | 3 | 4 | 36 | QA Leader | 2022-06-22 | Making testing center of development work Every feature development has to come with testing in order to ship | Development work has not started | Open
Integration and deployment | Not enough time for integration and deployment | Project not deployed if this was a non essential feature | 3 | 2 | 3 | 36 | Configuration Management Leader | 2022-06-22 | Create deployment pipeline early in the development process. | Development work has not started | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.