## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 32 | team leader and all members | 2022-05-29 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far. The team is appropriately staffed and based on current progress to finish the project | Closed
| Add new team members | New students joined the team in the middle of development | 1 | 3 | 3 | 45 | team leader and all members | 2022-05-29 | Keep good project documentation New engineers will work with a dedicated senior engineer | We are midway in the class and likely won't be getting new students in the group. | Closed
| Lack of motivation or responsibility | One or more students are not actively participating in the project | 1 | 5 | 3 | 15 | team leader and all members | 2022-05-29 | Opportunities for everyone to learn Everyone to work on something they are interested Practice the sprint rituals which keeps the team engaged | Everyone is engaged to a certain degree. The majority of the group is super motivated to complete the project. | Closed
Communication | Duplicate work | Two or more students are working on the same tasks without coordination hence duplicated work. | 2 | 3 | 3 | 36 | Team Leader | 2022-06-22 | Create a detailed project plan and get buy-in from the team Assign tasks to individuals during Sprint Planning Every tasks in the Sprint is assigned to a specific person in PivotalTracker | Sprint planning for iteration 2 (as we did for iteration 1) and tasks assignment to ensure everyone understand what they and others are working on. | Open
| Useless work | Students work cannot be used in the project. | 3 | 3 | 3 | 27 | team leader and all members | 2022-05-30 | Architecture and design session before we start big chuck of work Student to write design document about how they are going to implement a feature Students to break down feature work into small parts and complete them which will give enough opportunity to catch if we are build the product right | We have good example of patterns to use with documentation for team members to follow. Encourage early PR with small and complete feature to avoid students going down the wrong path and waisting time. | Open
Requirements | Unclear requirements | Requirements about a feature are not well understood. | 3 | 4 | 2 | 12 | team leader and all members | 2022-05-30 | Sprint review meeting with stakeholders Constant communication with stakeholders Stakeholders to review all requirements and answer questions. | The project essential functional requirements are now being finalized. | Open
| Scope creep | Significant increase in the a feature scope than anticipated. | 4 | 4 | 4 | 16 | team leader and all members | 2022-05-30 | Meeting with stakeholders about increase of scope which might impact project schedule Dropping some of essential features Alternative technical solutions | Build the application GUI is now an essential feature. | Open
| Constant requirements changes | Stakeholders keep changing the project requirements. | 5 | 4 | 4 | 8 | team leader and all members | 2022-06-22 | Favor generic solutions so they are adaptable Embrace the change and build the product using appropriate design patterns Emphasize the communication with stakeholders to ensure requirements are well understood | Build the application GUI is now an essential feature. | Open
Management | Improper task assignments | Tasks assigned to team members does not fit their skillset or preferrence. | 3 | 3 | 3 | 27 | Team Leader | 2022-06-22 | Sprint planning meeting and discuss tasks before they are assigned | We continue to run Sprint planning before each iteration. | Open
| Improper planning | No timeline or tasks breakdown | 1 | 2 | 3 | 60 | Team Leader | 2022-05-22 | Project scoping and estimation Detailed tasked break down | The team was able to over achieve during iteration 1. We need to keep the pace sustainable while planning iteration 2. | Open
Technology competence | Not familiar with the framework used | Team members who are not familiar with the framework and other techologies used to development project. | 2 | 3 | 3 | 36 | Design and Implementation Leader | 2022-05-22 | Plan time for tutorial about the framework No indroducing new techologies late in the project Use widely support technologies so students can find help online if they are blocked Learn React. | We have selected the Spring framework and everyone on the team is somewhat familiar. Moreover, they all know Java. We have made UI for the app an essential feature and the majority of the group is not familiar with React. It has been choosen as the front technology. | Open
| Not familiar with unit testing | Students who are new to unit testing | 4 | 2 | 3 | 24 | QA Leader | 2022-06-04 | Plan time for unit testing tutorial (JUnit 5) Learn by doing as each feature implementation will require unit tests | Development work has not started | Open
Design and implementation | Improper design | Implemented a design that is not flexible or generic enough. | 3 | 4 | 3 | 18 | Design and Implementation Leader | 2022-05-29 | Architecture and design session before we start big chuck of work | The project is following common patterns using proven architecture. | Closed
Testing | Not enough testing | Falling short of the planned test coverage for the project | 3 | 3 | 4 | 36 | QA Leader | 2022-06-22 | Making testing center of development work Every feature development has to come with testing in order to ship | There are good Unit testing for the backend but Unit testing for the UI has not started. Also, need to consider Integration tests. | Open
Integration and deployment | Not enough time for integration and deployment | Project not deployed if this was a non essential feature | 3 | 2 | 3 | 36 | Configuration Management Leader | 2022-05-29 | Create deployment pipeline early in the development process. | The project is deployed to both a development and production environment with GitHub auto deploy integration during iteration 1. | Closed
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.