## Summary-GroupIterationProgress
Team 1 - trackr
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks
0 | 05/10 - 05/15 | 1. Completed all deliverables for Iteration 0 2. Skeleton Spring Boot application and Swagger Document | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 81 | 79 | 2 | 39 | 7 | 0 | 8 | 3 | 14 | 8 | 0
1 | 05/17 - 05/29 | 1. Updated code with implementation from Iteration 1 stories, removed "Hello World" code. (add more detail like stories completed) 2. Created Docker deployment script for containerization 3. Set up Deployment environments for DEV and PROD using the Heroku platform 4. Established quick team response to new Pull Requests, and provide helpful and meaningful comments to improve code quality. | - All team members need to engage in some type of research for this iteration's development (Spring Boot, React, JWT tokens) which took away time from other tasks | - Based on professor's comments from Iteration 0, requirement priority was redefined to increase priority on the Web GUI stories. Workload needed to be adjusted. | - More stictly enforce daily standup updates - Add deployment step to Git merge process to make sure that new code doesn't break the build before being merged. - JS Code Sniff Pipeline to enforce code formatting | 6 | 22 | 0 | 0 | 0 | 197 | 189 | 8 | 84 | 8 | 13 | 51.5 | 13 | 11.5 | 8 | 0
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Timothy Flucker | Developed Sections 1, 2, 3, 6b | Created initial tasks for Iteration 0 activities and Lab1. | N/A | N/A | Helped create initial slide deck and provide content from my assigned SPPP sections. | Committed a basic Spring application which is to be used as a starting point for Iteration 1 development. | Created basic unit test in committed code to be used a reference for other team members. | N/A | Assisted Jean by providing standup updates and comments on documents. Helped setup Discord threads for Standup Notes and PR Requests to increase team organization.
Xiaobing Hou | Developed Section 5
Jean Dorancy | - Management Plan. - Git Branching Strategry. - Code Review Process. | - Created cores related to iteration 0 and completed them. - Created two stories in Pivotal Tracker which relates to delete and modify bank accounts | N/A | N/A | - Completed slide deck and recorded video prensentation for iteration 0. | - Docker setup and application deployment in development | N/A | - Created reposiotry, configured branch proctetion rules and merging strategy. - Also added .gitignore file and Pull Request template. Peformed code reviews. - Setup deployment to development with documentation. | - General coodination for the team. - Organized meetings. - Daily Scrum (in appropriate thread). - Run Sprint Planning | N/A
Weijie Liang | Developed Section 6 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Timothy Flucker | - Modified hours for stories in section 2 | - Added all stories for Iteration 1 - Begain adding stories for Iteration 2 | - Began providing content for document |  |  |  | Created unit tests using Mockito for Iteration 1 story development.. |  | - Provided standup updates to team members - Assisting team members with questions about development / coursework | - Created Code Walkthrough video for team members to explain Iteration 0 code base
Timothy Flucker | - Updated requirements section to more accurately reflect hours worked on Iteration 1 stories | - Began adding more stories for Iteration 2 | - Created initial content for document - added UML diagrams relevant to different sections | N/A | - Created slide deck for Iteration 1 presentation. Included agenda for a live demo. | - Created 5 APIs (Create User, Retrieve JWT token, Add Bank Account, Modify Bank Account, Deactivate Bank Account) - Implemented JWT token verification for all APIs | - Created unit tests for APIs developed in Iteration 1. - Implemented Mockito to mock database calls and prevent test data from being inserted into the database. |  | - Provided standup updates to team members - Assisting team members with questions about development / coursework - Provided feedback for multiple GitHub pull requests.
Jean Dorancy | - Updated Requirements - Updated Timeline - Resoved comments | - Created stories with detailed taks for my work | - React Container Pattern - Mockups for GUI | - Generated test converage report. | - Updated development completed to reflect the 3 categories of work completed. - Generated test coverage report and created slide. - Deployment overview slide - Added mockups to showcase next steps. | - Setup project frontend - Created project home page with user registration - Create login page with backend integration - README documentation about the setup, pattern used and steps for deploying etc. | - Updated unit tests for password min length - Fixed one test case about user controller - Manual testing for home page with user registration - Manual testing for login page | - Setup deployment to production - Configured GitHub integration with Heroku which provides auto deploy to production when merged to main and auto deploy to development when merged to development. - Heroku deploy tool to able to deploy a branch - Configured GitHub Action to run JavaScript code Sniff in a docker container (developed script) - Configured GitHub Repo to require branch deployment to development before any merge to protected branches (main or development) | - General coodination for the team. - Drive meetings agenda. - Daily Scrum (in appropriate thread) - Code Reviews | README documentation with details to help folks onboard on their own.
Xiaobing Hou | N/A | Created five stories in Pivotal Tracker for the transaction management | N/A | N/A | N/A | Create five APIs for transaction management(include Create, modify, void, find by id, find all transaction) | Created unit tests using Mockito for Iteration 1 transaction storys development. | Create Heroku team, and development pipeline | N/A | Update postman collection file
Weijie Liang | N/A | -Created stories for my functions | N/A | Write the first version of Test Summary, Test Report and Test Metric | N/A | N/A | -Create unit test for APIs -Manual testing for login page | N/A | N/A | N/A

## Jean Dorancy
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/16 | 23 | 21 | 2 | 0 - Studied the course module and watched all the videos. 1 - Reviewed and discussed project requirements proposed by Tim 5 - Coodinated team meetings, Work on SPPP, Risk Management, Estimation and presentation. 6 - Setup Git repository with merge and protection rules. | 8 | 2 | 0 | 0 | 0 | 10 | 1 | 0 | 1. Write 3 sections of SPPP 2. Completed Lab 1 3. Completed project presentation 4. Completed risk management sheet 5. Created estimation sheet 6. Created Pull Request Template | 1. It's was quite a bit of materials to study | 1. Frontload module stuying early in the week | 0. Organize Sprint Planning for iteration 1 1. Study Module 2 3. Work on implementation after tasks assignments | 35
2 | 05/17 - 05/23 | 27 | 25 | 2 | 0 - Studied course module, completed lab 2 and a course about Spring Boot on Plurasight 1 - Discussed moving GUI as an essential feature. 2 - Comments and feedback via code reviews. 3 - Dockerize the application. 4 - Test the user api locally and in development. 5 - Organise and drive team meetings (spring planning). 6 - Deployed the application on Heroku as Docker container. | 12 | 1 | 2 | 6 | 1 | 2 | 1 | 0 | 1. Docker setup and application deployment in development. 2. Readme documentation about Docker and deploying to development. 3. Code reviews. | Change in requirements to make GUI essential features. | Setup the project with Webpack and React this week to enable the team to start developing the UI. | 0. Complete deliverables for iteration 1 1. Setup project with React and Webpack 2. Create the user registration page 3. Code reviews | 35
3 | 05/23 - 05/30 | 05/23 - 05/30 | 37 | 2 | 0 - Reviewing React fundamentals and learning about React Router DOM, Webpack, Spring Boot Hot Reload, React Boostrap, Formik, Yup, React Container Pattern and class notes. 1 - Requirements for home page with user creation and User login page. 2 - Review Tim contribution to SDD. 3 - Develop frontend setup, home page with user creation and login page. 4 - UI manual tests and fixed 2 backend unit tests and added one. 5 - General team coordination with meetings 6 - Deploy to production, added GitHub integration with Heroku, added code JS sniff pipeline as GitHub action running a docker container. | 15 | 1 | 1 | 15 | 2 | 1 | 2 | 0 | 1. Setup project frontend with React 2. Home page with user registration 3. Login page 4. SPPP Updates in timeline 5. README in the repo 6. Deployment with GitHub Integration 7. JS Code Sniff Pipeline 8. Code reviews 9. Document reviews 10. Risk Management Updates | A lot of materials to study and get productive in the UI. | UI development is on track. | 0. Create user dashboard page 1. Create user profile page 2. Add Jest Unit tests for frontend components 3. Add pipeline to run JS tests on PR 4. Add pipeline to run Java tests on PR 5. Add pipeline to run static analysis on PR with SonarQube | 40

## Timothy Flucker
Your Lead Roles: Backup Project Leader, Design and Implementation Leader + Requirements Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10 - 05/15 | 20 | 18 | 2 | 0 - Reviewing course materials and documents, read module notes + chapters 1 - Define High-level requirements based on initial project proposal to team 3 - Created Spring Boot "Hello World" application 4 - Developed basic unit test in "Hello World" application 5 - Created Discord threads, and provided regular updates | 10 | 5 | 0 | 8 | 1 | 1 | 0 | 0 | 1. Wrote 3 sections of SPPP 2. Committed code for "Hello World" Spring Boot application 3. Provided content and comments for Iteration 0 presentation. 4. Created Discord threads and participated in group discussions and meetings. |  |  | 0 - Continue with module notes and reviewing course materials 1 - Define Requirements for Iteration 1, input these into PivotalTracker 2 - Create design document template for team to use 3 - Develop Iteration 1 requirements related User Management, H2 Database configuration, and Bank Account Management 4 - Create more varied unit tests (api logic, validation, entity tests) 5 - Continue providing updates and comments as necessary. | 20
2 | 05/16 - 05/22 | 20 | 30 | 2 | 0 - Learning about how to implement JWT tokens + Mockito, reading module notes and assigned chapters) 1 - Redefining requirements in SPP, adding all stories for Iteration 1 into Pivotal Tracker 2 - Design assigned stories (Create User, Create Bank Account, Modify Bank Account, Delete Bank Account APIs) 3 - Implementing Create User, Create Bank Account APIs 4 - Creating unit tests (with Mockito) for Create User + Create Bank Account APIs 5 - Group meetings, discord chat standup updates, communicating with team members to answer questions and notify them about blockers | 15 | 3 | 2 | 10 | 3 | 2 | 0 | 0 | 1. Began adding content to SDD 2. Updated SPP document with more accurate hours 3. Updating source code with new API implementations | I'm doing a lot of the back-end development work and I am unclear how much front-end work I will need to complete. I need to talk with the team members to more evenly distribute work and to ensure that scope creep does not create more work for us than necessary. | Discuss with team members on how to more evenly distribute work. | 0 - Review package by layer vs. package by feature 1- continue adding stories to backlog for Iteration 2 + 3, add stories to SPP as necessary 2 - Continue designing modify + delete Bank account stories 3 - implement modify + delete bank account stories 4 - continue writing unit tests for implemented stories 5 - continue providing updates on development and assisting team members as necessary | 25
3 | 05/23 - 05/29 | 20 | 20 | 2 | 0 - Reviewing course materials, learning about UML graphs 1 - Updating functional stories in the SPPP, determining which stories will be done in Iteration 2 3 - Bug fixes and code reviews for development from other team members. 4 - Updating unit tests, updating Postman JSON collection 5 - Group meetings, discord chat standup updates, communicating with team members to answer questions and participate in code reviews. 6 - reviewing Heroku deployment and Docker scripts creating by Jean. | 8 | 3 | 0 | 4 | 2 | 2 | 1 | 0 | 1. Provided small updates to SPPP document, re-arranged and updated content of the "requirements" section of the SPPP 2. Added initial content for the SDD document 3. Created presentation slides for Iteration 1 | I'll be on vacation from 05/30 - 06/06. I need to update my team and determine what work I can reasonably accomplish with severly limited hours and without much communication with the team. | I have updated my team, notifying them of my vacation. I will assign myself work in Pivotal Tracker for the first week of Iteration 2 and provide updates via discord. | 0 - review how to establish an HTTPS connection for the application 1 - Add stories for iteration 2 into the Pivotal Tracker in preparation for sprint planning, Update sections in SPPP and SDD as the application evolves 3 - Finish developing APIs, refactor project to "package by function", add HTTPS connection 4 - add more unit tests for apis and security features 5 - Continue providing updates on development and assisting team members as necessary | 30
4 | 05/30 - 06/05
5 | 06/06 - 06/12
6 | 06/13 - 06/19

## Xiaobing Hou
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/15 | 25 | 12 | 2 | 0 - learn git, Spring boot framework, Heroku, read several tutorials 6 - set up git, IDE, java | 16 | 0 | 0 | 0 | 2 | 2 | 5 | 0 | 1. Write section5 for SPPP 2. Set up git, commit a test message on git |  |  | 0 - Continue with module notes and reviewing course materials 1 - Continue learn Spring Boot framework and Heroku 2 - Try to code use Spring Boot framework and do a simple program | 30
2 | 05/16 - 05/22 | 20 | 30 | 2 | 0 - Learn Spring boot framework, Heroku, read several tutorials 2 - Design assigned stories (Create Transaction, find transaction, modify transaction APIs) 5 - Group meetings, discord chat standup updates, communicating with team members | 20 | 0 | 8 | 0 | 0 | 2 | 0 | 0 | 1. Develop source code with new API implementations |  |  | 0-Finish the Transaction APIs | 30
3 | 05/23 - 05/29 | 25 | 25 | 2 | 0 - Reviewing course materials, finish quiz 1, and learning about UML graphs 3 - Finish five API functions about transaction 4 - Updating unit tests, updating Postman JSON collection 6 - reviewing Heroku deployment and try to deploy a branch into development app | 7 | 0 | 0 | 11 | 5 | 0 | 2 | 0 | 1 - Finish five APIs functions about transaction 2 - Updating unit tests, updating Postman JSON collection |  |  | 0 - Reviewing course materials 2 - Learn some skills about React | 25

## Weijie Liang
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/15 | 8 | 7.5 | 0.5 | 0 - learn git and springboot, review class material, read Module 1 6 - set up git, Java | 5 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 1. Write Section 6 of SPPP 2. Set up git, commit README.MD on git |  |  | 1. Continue reviewing class material and Modules 2. Learn about Springboot framework 3. Try to write basic Springboot based code | 28
2 | 05/16 - 05/22 | 10 | 8.5 | 1.5 | 0 - learn springboot and react, review class material, and read Module 2 3 - create find bank account API 5 - group meeting | 5 | 0 | 0 | 3.5 | 0 | 1.5 | 0 | 0 | 1. Begin writing find bank account API | Not much experience in front-end React architecture development, still need to spend time to learn and communicate with group members | Spend time learning React and Springboot | 1. Continue reviewing class material and Modules 2. Learn about Springboot and React 3. Try to write basic React | 30
3 | 05/23 - 05/30 | 17 | 15 | 2 | 0 - review class material, read about Docker, UML 3 - finish developing 2 bank account APIs 4 - update unit tests for APIs 5 - group meeting and discord chat 6 - deploy branch to Heroku | 2 | 0 | 0 | 8 | 4 | 2 | 1 | 0 | 1. Finish 2 bank account APIs 2. Write the first version of the STD document 3. Update unit tests | The weak basic knowledge made the development time I needed much longer | Keep learning on Springboot and React to make sure I can keep on track | 1. Continue reviewing class materials and learn about React 2. Continue learning about React | 25